## Android
Test case_ID | Req_id | Test Case Summary | Adroid App Test Steps | iOS Shell App Test Steps | Web Test Steps | iOS Full App Test Steps | Expected Results | Android Status | iOS Shell App Status | Web Status | iOS Full App Status | Defect_ID | Comments
LOCH_01 | FUNC-6.1 Location History - The system shall support the ability to view location history for the prior 7 days. | Location History > verify history is available for 7 days | Login as an Admin into Android v6 App | Login as an Admin in ios shell app | Launch web URL and Login as Admin | Login as an Admin into iOS Full App App | App should show the location history for 7 days for all group member | PASS |  | PASS
|  |  | Go to Members screen | Go to members screen | Go to members screen | Go to Members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | Validate the history is available for 7 days for any member | Validate the history is available for 7 days for any member | Validate the history is available for 7 days for any member | Validate the history is available for 7 days for any member
LOCH_01 | Location History - The system shall support the ability to view location history for the prior 7 days. | Location History > verify history for 7 Days | Login as an Admin into Android v6 app | Login as an Admin into Android v6 app | Login as an Admin into Android v6 app | Login as an Admin into Android v6 app | App should show the location history for the prior 7 days for Admin | PASS | PASS | PASS | PASS
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | View the history of any member | View the history of any member | View the history of any member | View the history of any member
LOCH_02 |  | Location History > Scroller > Verify page scroller in location history | Login as an Admin into Android v6 app | Login as an Admin in iOS Shell app | Launch web URL and Login as Admin | Login as an Admin in iOS Full app | Scroller should be available and should work without issue | PASS | PASS | PASS | PASS
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | view the location history till the bottom of page | view the location history till the bottom of page | view the location history till the bottom of page | view the location history till the bottom of page
LOCH_03 |  | Location History > Server Time > Verify history time syncs with server time | Login as an Admin into Android v6 app | Login as an admin in iOS Shell app | Launch web URL and Login as Admin | Login as an admin in iOS Full app | App should update the information as per the server date and time. | PASS | PASS | PASS | PASS
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | view the time and history of the users | view the time and history of the users | view the time and history of the users | view the time and history of the users
|  |  | Change the Admin device time to future/past | Change the admin device time to future/past | Change the admin device time to future/past | Change the admin device time to future/past
|  |  | Save the time settings | Save time Settings | Close the browser | Close the browser
|  |  | Launch the VZFL application | Launch the VZFL application | Launch web URL and Login as Admin | Launch the VZFL application
|  |  | view the history of all the members | view the history of all the members | view the history of all the members | view the history of all the members
LOCH_04 |  | Location History > Verify location history days format | Login as an Admin into Android v6 App | Login as an admin in iOS Shell App | Launch web URL and Login as Admin | Login as an admin in iOS Full App | App should show the date wise history starts from 'Today' and then "yesterday, rest of dates for past 5 dates" | Pass | PASS | PASS | PASS
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | View the history of the member | View the history of the member | View the history of the member | View the history of the member
|  |  | Observe the order of the history days and dates | Observe the order of the history days and dates | Observe the order of the history days and dates | Observe the order of the history days and dates
Note: Please execute in Portrait and Landscape orientation
LOCH_05 |  | Location History > Verify history expansion for individual day | Login as an Admin into Android v6 App | Login as an admin in iOS Shell App | Launch web URL and Login as Admin | Login as an admin in iOS Full App | At Step4, App should show the history for 7 days | Pass | PASS | PASS | PASS
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen | At step5, history date should be expanded and displays travelled locations history
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | View the history of the member | View the history of the member | View the history of the member | View the history of the member
|  |  | Tap on + symbol for expanding history date | Tap on + symbol for expanding history date | Tap on + symbol for expanding history date | Tap on + symbol for expanding history date
LOCH_06 |  | Location History > Verify collapsing history for individual day | Login as an Admin into Android v6 App | Login as an admin in iOS Shell App | Launch web URL and Login as Admin | Login as an admin in iOS Full App
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen | At Step4, app should show the history for 7 days | Pass | PASS | PASS | PASS
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member | At Step5, history date should be collapsed and should hide locations history
|  |  | View the history of the member | View the history of the member | View the history of the member | View the history of the member
|  |  | Tap on - symbol for collapsing history date | Tap on - symbol for collapsing history date | Tap on - symbol for collapsing history date | Tap on - symbol for collapsing history date
LOCH_07 |  | Location History > Verify 'stop' status when device is near one or more geofences | Login as an Admin into Android v6 App | Login as an admin in iOS Shell App | Launch web URL and Login as Admin | Login as an admin in iOS Full App | For step5, app should show user is "Near <place.name>" in the location history. | Pass | PASS | PASS | PASS
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | View the history for the current day | View the history for the current day | View the history for the current day | View the history for the current day
|  |  | Move the member device to any place(geofence) | Move the member device to any place(geofence) | Move the member device to any place(geofence) | Move the member device to any place(geofence)
|  |  | Make the member device not to move for longer time | Make the member device not to move for longer time | Make the member device not to move for longer time | Make the member device not to move for longer time
LOCH_08 |  | Location History > Verify 'stop' status when device is near to POI | Login as an Admin into Android v6 App | Login as an admin in iOS Shell App | Launch web URL and Login as Admin | Login as an admin in iOS Full App | After step5, app should show user is "Near <reverse geocoded address>" in the location history | Pass | PASS | PASS | PASS
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | View the history for the current day | View the history for the current day | View the history for the current day | View the history for the current day
|  |  | Move the member device to any POI | Move the member device to any POI | Make sure member device is not near to any POI | Move the member device to any POI
|  |  | Make sure the device is not moving from that POI | Make sure the device is not moving from that POI | Note: Please execute in Portrait and Landscape orientation | Make sure the device is not moving from that POI
LOCH_09 |  | Location History > Verify 'stop' status when device is not near to POI | Login as an Admin into Android v6 App | Login as an admin in iOS Shell App | Launch web URL and Login as Admin | Login as an admin in iOS Full App | After step5, app should not show user is "Near <reverse geocoded address>" in the location history | Pass | PASS | PASS | PASS
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | View the history for the current day | View the history for the current day | View the history for the current day | View the history for the current day
|  |  | Make sure member device is not near to any POI | Make sure member device is not near to any POI | Make sure member device is not near to any POI | Make sure member device is not near to any POI
LOCH_10 |  | Location History > Verify 'moving' status in the member history | Device1 : Login as an Admin into Android v6 App | Device1 : Login as an Admin into iOS shell App | Launch web URL and Login as Admin | Device1 : Login as an Admin into iOS Full App | For step4, App should show the current location of user | Pass | PASS | PASS | PASS
|  |  | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | For step5, user status should update to 'driving/moving/walking'(depends on speed) till device reach the next destination along time duration
|  |  | Device2 : Move the device to some other location | Device2 : Move the device to some other location | Device2 : Move the device to some other location | Device2 : Move the device to some other location | For step7, location status should be updated with latest location information in history with text "At <place.name>"
|  |  | Device1 : Verify the status of the device in the history | Device1 : Verify the status of the device in the history | Verify the status of the device in the history in Web Client | Device1 : Verify the status of the device in the history
|  |  | Device2 : Reach the destination | Device2 : Reach the destination | Device2 : Reach the destination | Device2 : Reach the destination
|  |  | Device1 : Verify the location history of the member | Device1 : Verify the location history of the member | Verify the location history of the member in Web Client | Device1 : Verify the location history of the member
LOCH_11 |  | Location History > Verify location history header shows the user latest location/last known location | Device1 : Login as an Admin into Android v6 App | Device1 : Login as an Admin into iOS shell App | Launch web URL and Login as Admin | Device1 : Login as an Admin into iOS Full App | For Step4, App should show the coarse location and display like member is "near_<place address>" in both header and also in history grid | Pass | PASS | PASS | PASS
|  |  | Device1: Create a place 'Home' through admin | Device1: Create a place 'Home' through admin | Create a place 'Home' through admin | Device1: Create a place 'Home' through admin | For Step7, App should show the members location like member is "at_<place address>" in both header and also in history grid
|  |  | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app
|  |  | Device2 : Move the device to place 'Home' | Device2 : Move the device to place 'Home' | Device2 : Move the device to place 'Home' | Device2 : Move the device to place 'Home'
|  |  | Device1 : Verify the location history of the member | Device1 : Verify the location history of the member | Verify the location history of the member in Web Client | Device1 : Verify the location history of the member
|  |  | Device1 : Verify the member location in the header description | Device1 : Verify the member location in the header description | Verify the member location in the header description in Web Client | Device1 : Verify the member location in the header description
LOCH_12 |  | Location History > Verify grouping of 'moves' between closer geofences | Device1 : Login as an Admin into Android v6 App | Device1 : Login as an Admin into iOS Shell App | Launch web URL and Login as Admin | Device1 : Login as an Admin into iOS Full App | App should club all the moves and should show all the geofences list one after the another with out any move status in between all the geofences | Pass | Pass | PASS | Paused
|  |  | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app
|  |  | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius)
|  |  | Device2: Move the device to another geofence which is less than 300 mts away from pizza and stay for more than 10 mins Eg: coffebucks (300 meters radius) | Device2: Move the device to another geofence which is less than 300 mts away from pizza and stay for more than 10 mins Eg: coffebucks (300 meters radius) | Device2: Move the device to another geofence which is less than 300 mts away from pizza and stay for more than 10 mins Eg: coffebucks (300 meters radius) | Device2: Move the device to another geofence which is less than 300 mts away from pizza and stay for more than 10 mins Eg: coffebucks (300 meters radius)
|  |  | Device2: Move the device to another geofence which is less than 300 mts away from coffee bucks and stay for more than 10 mins Eg: movie (300 meters radius) | Device2: Move the device to another geofence which is less than 300 mts away from coffee bucks and stay for more than 10 mins Eg: movie (300 meters radius) | Device2: Move the device to another geofence which is less than 300 mts away from coffee bucks and stay for more than 10 mins Eg: movie (300 meters radius) | Device2: Move the device to another geofence which is less than 300 mts away from coffee bucks and stay for more than 10 mins Eg: movie (300 meters radius)
LOCH_13 |  | Location History > Verify 'move' status between two geofence which are residing more than 1000mts | Device1 : Login as an Admin into Android v6 App | Device1 : Login as an Admin into iOS shell App | Launch web URL and Login as Admin | Device1 : Login as an Admin into iOS Full App | App should display both the geofences by separating with 'moved' status between two locations | Pass | Pass | PASS | Paused
|  |  | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app
|  |  | Device2: Move the device to any geofence and stay for more than 30 mins Eg: Starbucks | Device2: Move the device to any geofence and stay for more than 30 mins Eg: Starbucks | Device2: Move the device to any geofence and stay for more than 30 mins Eg: Starbucks | Device2: Move the device to any geofence and stay for more than 30 mins Eg: Starbucks
|  |  | Device2: Move the device to another geofence which is more than 1000 mts away from Starbucks and stay for more than 10 mins Eg: movie theater | Device2: Move the device to another geofence which is more than 1000 mts away from Starbucks and stay for more than 10 mins Eg: movie theater | Device2: Move the device to another geofence which is more than 1000 mts away from Starbucks and stay for more than 10 mins Eg: movie theater | Device2: Move the device to another geofence which is more than 1000 mts away from Starbucks and stay for more than 10 mins Eg: movie theater
LOCH_14 |  | Location History > Verify grouping of 'Stops' with in single geofence | Device1 : Login as an Admin into Android v6 App | Device1 : Login as an Admin into iOS Shell App | Launch web URL and Login as Admin | Device1 : Login as an Admin into iOS Full App | At Step3, In Device1 or web client , member history should show a stop status at geofence pizza | Pass | Pass | PASS | Paused
|  |  | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app
|  |  | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | At step4, In Device1, app should group the moves with in the geofence
|  |  | Device2: Move the device with in geofence 100 to 150 mts range | Device2: Move the device with in geofence 100 to 150 mts range | Device2: Move the device with in geofence 100 to 150 mts range | Device2: Move the device with in geofence 100 to 150 mts range | At step5, In Device1, members history should update the new stop status with new geofence
|  |  | Device2: Move the device out side of the geofence more than 300 mts | Device2: Move the device out side of the geofence more than 300 mts | Device2: Move the device out side of the geofence more than 300 mts | Device2: Move the device out side of the geofence more than 300 mts | At step6, device stationary status should show as stop status if the device doesn't move
|  |  | Device2: Keep the device stationary for more than 10 minutes | Device2: Keep the device stationary for more than 10 minutes | Device2: Keep the device stationary for more than 10 minutes | Device2: Keep the device stationary for more than 10 minutes
LOCH_15 |  | Location History > Verify grouping of 'Stops' in more geofences which are overlapped | Device1 : Login as an Admin into Android v6 App | Device1 : Login as an Admin into iOS Shell App | Launch web URL and Login as Admin | Device1 : Login as an Admin into iOS Full App | At Step3, In Device1, member history should show a stop status at geofence pizza | Pass | Pass | PASS | Paused
|  |  | Device2 : Login as Member to v6 app | Device2: Login as member | Device2: Login as member | Device2 : Login as Member to v6 app | At step4, In Device1, app should group the moves with in the geofence
|  |  | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | Device2: Move the device to any geofence and stay for more than 10 mins Eg: Pizza (300 meters radius) | At step5, In Device1, members history should update the new stop status with new geofence
|  |  | Device2: Move the device with in geofence 100 to 150 mts range | Device2: Move the device with in geofence 100 to 150 mts range | Device2: Move the device with in geofence 100 to 150 mts range | Device2: Move the device with in geofence 100 to 150 mts range | Till step6, All stops should be created immediately one above another with out any move status between the stops
|  |  | Device2: Move the device to next geophone just which resides immediately next Pizza location(more than 300 mts and less than 600 mts) | Device2: Move the device to next geofence just which resides immediately next Pizza location(more than 300 mts and less than 600 mts) | Device2: Move the device to next geofence just which resides immediately next Pizza location(more than 300 mts and less than 600 mts) | Device2: Move the device to next geofence just which resides immediately next Pizza location(more than 300 mts and less than 600 mts) | At step7, app should update the move status should be updated once the user leaves the geofence
|  |  | Device2: Move the device to next geofence location(more than 600 mts and less than 900 mts) | Device2: Move the device to next geofence location(more than 600 mts and less than 900 mts) | Device2: Move the device to next geofence location(more than 600 mts and less than 900 mts) | Device2: Move the device to next geofence location(more than 600 mts and less than 900 mts)
|  |  | Device2: Take the device out side of the geofence completely | Device2: Take the device out side of the geofence completely | Device2: Take the device out side of the geofence completely | Device2: Take the device out side of the geofence completely
LOCH_16 | VZFL-204, VZFL-977 | Location History > Verify stop and move actions are shown as a polyline with circle on all stops. | Device1 : Login as an Admin into Android v6 App | Device1 : Login as an Admin into iOS Shell App | Launch web URL and Login as Admin | Device1 : Login as an Admin into iOS Full App | For step5, app should show blue color polyline while moving and blue color dotted circle for stop status. | Pass | Pass | PASS | PASS
|  |  | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app | Device2 : Login as Member to v6 app
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | Device1 : View the history of any day | Device1 : View the history of any day | Web : View the history of any day | Device1 : View the history of any day
|  |  | Device1 : view the polylines for stops and moves | Device1 : view the polylines for stops and moves | Web : view the polylines for stops and moves | Device1 : view the polylines for stops and moves
|  |  | Note: Please execute in Portrait and Landscape orientation | Note: Please execute in Portrait and Landscape orientation | Note: Please execute in Portrait and Landscape orientation | Note: Please execute in Portrait and Landscape orientation
LOCH_17 |  | Location History > Verify user can view location on map | Login as an Admin into Android v6 App | Login as an Admin into iOS Shell App | Login as an Admin into Web URL | Login as an Admin into iOS Full App | After step5, location should be viewed on the map | Pass | Pass | Pass | PASS
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | Expand the history of any day | Expand the history of any day | Expand the history of any day | Expand the history of any day
|  |  | Tap on any location | Tap on any location | Tap on any location | Tap on any location
LOCH_18 |  | Location History > Tip > Verify the tip for the devices which VZFL app is not installed | Device1: Login as an admin into Android v6 App | Device1: Login as an admin into iOS Shell App | Login as an Admin into Web URL | Device1: Login as an admin into iOS Full App | App should show a tip 'Area locations only' and on touching red color alert icon then app should show "This phone does not have VZFL installed, limiting location precision. If this phone is an android device, send the app." and with "send app" link should be available to the particular member | Pass | Pass | Pass | PASS
|  |  | Device2: Ensure member device is not installed VZFL app | Device2: Ensure member device is not installed VZFL app | Device2: Ensure member device is not installed VZFL app | Device2: Ensure member device is not installed VZFL app
|  |  | Device1: Go to members screen | Device1: Go to members screen | Web : Go to members screen | Device1: Go to members screen
|  |  | Device1: Tap on member (Device2) for history | Device1: Tap on member (Device2) for history | Web : Tap on member (Device2) for history | Device1: Tap on member (Device2) for history
|  |  | Device1:View the tip in the location history | Device1:View the tip in the location history | Web :View the tip in the location history | Device1:View the tip in the location history
LOCH_19 |  | Location History > Tip > Verify the tip for the devices which VZFL app is installed | Device1: Login as an admin into Android v6 App | Device1: Login as an admin into iOS Shell App | Login as an Admin into Web URL | Device1: Login as an admin into iOS Full App | App should show a label 'Area locations' and should show a stating "Family locator was unable to obtain a precise location for this phone" for the particular member. | Pass | Pass | Pass | PASS
|  |  | Device2: Ensure member device is installed VZFL app | Device2: Ensure member device is installed VZFL app | Device2: Ensure member device is installed VZFL app | Device2: Ensure member device is installed VZFL app
|  |  | Device1: Go to members screen | Device1: Go to members screen | Web : Go to members screen | Device1: Go to members screen
|  |  | Device1: Tap on member (Device2) for history | Device1: Tap on member (Device2) for history | Web : Tap on member (Device2) for history | Device1: Tap on member (Device2) for history
|  |  | Device1:View the tip in the location history | Device1:View the tip in the location history | Web :View the tip in the location history | Device1:View the tip in the location history
LOCH_20 |  | Location History > Tip > Verify the tip for the devices when members location service is unreachable | Device1: Login as an admin into Android v6 App | Device1: Login as an admin into iOS Shell App | Login as an Admin into Web URL | Device1: Login as an admin into iOS Full App | App should show a tip(Area Location) for first time stating ' Family locator was unable to obtain precise location for this phone' | Pass | Pass | Pass | PASS
|  |  | Device2: Ensure member device location services is unreachable but not turned off. | Device2: Ensure member device location services is unreachable but not turned off. | Device2: Ensure member device location services is unreachable but not turned off. | Device2:Ensure member device location services is unreachable but not turned off.
|  |  | Device1: Go to members screen | Device1: Go to members screen | Web : Go to members screen | Device1: Go to members screen
|  |  | Device1: Tap on member (Device2) for history | Device1: Tap on member (Device2) for history | Web : Tap on member (Device2) for history | Device1: Tap on member (Device2) for history
|  |  | Device1:View the tip in the location history | Device1:View the tip in the location history | Web :View the tip in the location history | Device1:View the tip in the location history
LOCH_21 |  | Location History > Tip > Verify the tip for the devices which are not compatible for VZFL | Device1: Login as an admin into Android v6 App | Device1: Login as an admin into iOS Shell App | Login as an Admin into Web URL | Device1: Login as an admin into iOS Full App | App should show a tip(Area Locations only) for first time stating ' phone does not have family locator installed, limiting location precision'. App should show 'Send app / cancel' popup window stating 'vzfl app is currently available for android phones only' | Pass | Pass | Pass | PASS
|  |  | Device2: Ensure member device doesn't support vzfl (Non-Android phones) | Device2: Ensure member device doesn't support vzfl (Non-Android phones) | Device2: Ensure member device doesn't support vzfl (Non-Android phones) | Device2:Ensure member device doesn't support vzfl (Non-Android phones).
|  |  | Device1: Go to members screen | Device1: Go to members screen | Web : Go to members screen | Device1: Go to members screen
|  |  | Device1: Tap on member (Device2) for history | Device1: Tap on member (Device2) for history | Web : Tap on member (Device2) for history | Device1: Tap on member (Device2) for history
|  |  | Device1:View the tip in the location history | Device1:View the tip in the location history | Web :View the tip in the location history | Device1:View the tip in the location history
LOCH_22 |  | Location History >Detail card > Validate the detail card of a user | Device1: Login as an admin into Android v6 App | Device1: Login as an admin into iOS Shell App | Device1: Login as an admin into Web URL | Device1: Login as an admin into iOS Full App | App should show the detail card by opening the location history and shows the location details along with mini map. | Pass | Pass | Pass | PASS
|  |  | Go to member profile | Go to member profile | Go to member profile | Go to member profile
|  |  | Tap on any member to view the detail card of a members location details | Tap on any member to view the detail card of a members location details | Tap on any member to view the detail card of a members location details | Tap on any member to view the detail card of a members location details
LOCH_23 |  | Location History > App2App > Navigation > Verify the navigation functionality | Ensure that VZ Navigator app is installed on device | Ensure that VZ Navigator app is installed on device | NA | Ensure that VZ Navigator app is installed on device | At Step5, If the member location shows 'Area location/Area location only' then Navigation button should be in disabled mode | Fail | Fail | NA | Fail | VZFL-745
|  |  | Login as an admin into Android v6 App | Login as an admin into iOS Shell App |  | Login as an admin into Android v6 App | After Step6, VZ navigator app should be launched and navigates to the member location
|  |  | Go to members screen | Go to members screen |  | Go to members screen
|  |  | Tap on any member | Tap on any member |  | Tap on any member
|  |  | Ensure that member is in precise location(Eg: in Member screen no label should be shown like "Area location or Area location only") | Ensure that member is in precise location(Eg: in Member screen no label should be shown like "Area location or Area location only") |  | Ensure that member is in precise location(Eg: in Member screen no label should be shown like "Area location or Area location only")
|  |  | Tap on 'Navigation' at the bottom of the screen | Tap on 'Navigation' at the bottom of the screen |  | Tap on 'Navigation' at the bottom of the screen
LOCH_24 |  | Location History > Call > Verify the Call functionality | Login as an admin into Android v6 App | Login as an admin into iOS Shell App | NA | Login as an admin into iOS Full App | After Step4, app should use the device voice call feature and able to call the member | Pass | Pass | NA | Pass
|  |  | Go to members screen | Go to members screen |  | Go to members screen
|  |  | Tap on any member | Tap on any member |  | Tap on any member
|  |  | Tap on 'Call' at the bottom of the screen | Tap on 'Call' at the bottom of the screen |  | Tap on 'Call' at the bottom of the screen
|  |  | Note: Please execute in Portrait and Landscape orientation | Note: Please execute in Portrait and Landscape orientation |  | Note: Please execute in Portrait and Landscape orientation
LOCH_25 |  | Location History > Message(SMS) > Verify the message functionality | Login as an admin into Android v6 App | Login as an admin into iOS Shell App | NA | Login as an admin into iOS Full App | After Step5, app should ability to send SMS through message apps available in device | Pass | Pass | NA | Pass
|  |  | Go to members screen | Go to members screen |  | Go to members screen
|  |  | Tap on any member | Tap on any member |  | Tap on any member
|  |  | Tap on 'SMS' at the bottom of the screen | Tap on 'SMS' at the bottom of the screen |  | Tap on 'SMS' at the bottom of the screen
|  |  | Send the message to the member | Send the message to the member |  | Send the message to the member
LOCH_26 |  | Location History > Verify user can get location history when the network is lost | Login as an admin into Android v6 App | Login as an admin into iOS Shell App | Login as an admin into Web URL | Login as an admin into iOS Full App | At Step3, Admin should not update the location history of the member | Pass | Pass | Pass | Pass
|  |  | Device1: Disconnect the network | Device1: Disconnect the network | Web: Disconnect the network | Device1: Disconnect the network | At step4, Pending location history should be updated in admin device within system configured time
|  |  | Device 1:Login as member into Android v6 App | Device2 :Login as member into Android v6 App | Device 2:Login as member into Android v6 App | Device 1:Login as member into Android v6 App
|  |  | Device2: Move member device to various locations | Device2: Move member device to various locations | Device2: Move member device to various locations | Device2: Move member device to various locations
|  |  | Device2: Connect to the network | Device2: Connect to the network | Device2: Connect to the network | Device2: Connect to the network
|  |  | Device1:Check for the location history of the member | Device1:Check for the location history of the member | Web :Check for the location history of the member | Device1:Check for the location history of the member
LOCH_27 |  | Location History > Time Format > Validate Time format | Login as an admin into Android v6 App | Login as an admin into iOS Shell App | Login as an admin into Web URL | Login as an admin into iOS Full App | App should show 12 hours time format. | Pass | Pass | Pass | Pass
|  |  | On members screen Tap on any Member for history | On members screen Tap on any Member for history | On members screen Tap on any Member for history | On members screen Tap on any Member for history
|  |  | Expand any days history | Expand any days history | Expand any days history | Expand any days history
LOCH_28 |  | Location History > Verify 'stop' status when device was near one or more geofences later the geofences are deleted | Login as an admin into Android v6 App | Login as an admin into iOS Shell App | Login as an admin into Web URL | Login as an admin into iOS Full App | For step6, app should show user is at the address in the location history. | FAIL | FAIL | FAIL | FAIL
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | View the history for the current day | View the history for the current day | View the history for the current day | View the history for the current day
|  |  | Move the member device to any place(geofence) | Move the member device to any place(geofence) | Move the member device to any place(geofence) | Move the member device to any place(geofence)
|  |  | Make the member device not to move for longer time | Make the member device not to move for longer time | Make the member device not to move for longer time | Make the member device not to move for longer time
|  |  | Delete the place where the member is currently located | Delete the the place where the member is currently located | Delete the the place where the member is currently located | Delete the the place where the member is currently located
LOCH_29 |  | Location History > Verify profile pic should be shown in map in day hisptory detailed card | Login as an admin into Android v6 App | Login as an admin into iOS Shell App | Login as an admin into web URL | Login as an admin into iOS Full App | At Step 5 User profile picture should be shown in map in member day detailed card | FAIL | FAIL | FAIL | FAIL | VZFL-1395
|  |  | Go to members screen | Go to members screen | Go to members screen | Go to members screen
|  |  | Tap on any member | Tap on any member | Tap on any member | Tap on any member
|  |  | View the history for the current day | View the history for the current day | View the history for the current day | View the history for the current day
|  |  | Click on each location to see the location of the Member | Click on each location to see the location of the Member | Click on each location to see the location of the Member | Click on each location to see the location of the Member
|  |  | Validate the profile pic when location shows "near" | Validate the profile pic when location shows "near" | Validate the profile pic when location shows "near" | Validate the profile pic when location shows "near"
LOCH_30 |  | Location History > Verify profile pic and place icon should be overlapped when member is At saved place | Device 1: Login as an admin into Android v6 App | Device 1: Login as an admin into iOS Shell App | Web : Login as an admin into Web URL | Device 1: Login as an admin into iOS Full App | Member profile pic and Place icon should be overlapped in location History and indidual location | Pass | Pass | Pass | Pass
|  |  | Device2 : Login as an Member | Device2 : Login as an Member | Device2 : Login as an Member | Device2 : Login as an Member
|  |  | Device 1: create a place and save name as "Home" | Device 1: create a place and save name as "Home" | Web : create a place and save name as "Home" | Device 1: create a place and save name as "Home"
|  |  | Device 2 : Move the member to created place i.e Home | Device 2 : Move the member to created place i.e Home | Device 2 : Move the member to created place i.e Home | Device 2 : Move the member to created place i.e Home
|  |  | Device 1: View the history for the current day | Device 1: View the history for the current day | Web : View the history for the current day | Device 1: View the history for the current day
|  |  | Device 1 : Validate profile pic of member and place icon in Location history grid and also current day location | Device 1 : Validate profile pic of member and place icon in Location history grid and also current day location | Web : Validate profile pic of member and place icon in Location history grid and also current day location | Device 1 : Validate profile pic of member and place icon in Location history grid and also current day location